## Intro
Additional Project-Specific Liquidated Damages (APSLD)
Introduction
This process and the statewide tool were developed through a joint effort of the following TxDOT Districts and Divisions.
|  | Beaumont District |  | Dallas District | Houston District
|  | Corpus Christi District |  | San Angelo District | Construction Division
|  | Design Division |  | Compliance Division | General Counsel Division
Transportation Planning and Programming Division
Texas Transportation Code §223.012 and 43 TAC §9.22 require TxDOT to provide additional disincentives to assure the timely completion of projects. These will be included in the contract in the form of Additional Project-Specific Liquidated Damages (APSLD). TxDOT created Form 2699 in order to determine which projects present a significant impact to the traveling public and require APSLD. The University of Texas Center for Transportation Research (CTR) has calculated the value of time for passenger cars and trucks for use in the RUC calculator. These values will be updated by CTR on an annual basis.
The following are items to consider when evaluating a project for APSLD.
| – | APLSD should be evaluated using Form 2699 for every project except PM and 2R projects. APSLD evaluation is optional on PM and 2R projects.
| – | The District should ensure any APSLD do not conflict with other contracting techniques used on the project, such as lane rental fees, A + B bidding, milestones, lane assessment fees, or other incentive/disincentive clauses using RUC for determining value of time.
| – | The RUC Calculator and APSLD Handbook, including instructions for using the RUC calculator and examples for completing Form 2699, are accessible through the following webpages.
|  | – | RUC webpage: | https://www.txdot.gov/business/resources/highway/road-user-costs.html
–
–

## Traffic_Data
Obtaining Traffic Data for Road User Cost Calculation
Overview of Traffic Data and Sources
When performing a Road User Cost (RUC) calculation, an Average Daily Traffic (ADT) input is required. The Transportation Planning and Programming Division (TPP) recommends using Annual Average Daily Traffic (AADT) data for the ADT input, as this represents the certified and annualized traffic data. TPP recommends obtaining AADT from the Statewide Planning Map or STARS II system. The Statewide Planning Map is an easy-to-use resource for obtaining bi-directional (two-way) traffic data, as well as traffic data for frontage roads. It would therefore be sufficient for performing Road User Cost (RUC) calculations where directionality is not a requirement. Projects which require traffic data for a single direction could instead utilize the STARS II system. Sources of AADT data other than the Statewide Planning Map or STARS II could have other considerations or limitations that may not be suitable for RUC calculations.
In some cases, AADT from the Statewide Planning Map or STARS II may prove to be insufficient for RUC calculations. If traffic modeling or simulations are deemed necessary, users should contact personnel within their relevant district or division. If no internal personnel are available, consult with the relevant district about using a consultant to produce traffic models and simulations.
Comparing Traffic Data Sources
The APSLD handbook provides a detailed description of the two key sources for obtaining traffic data for a roadway. It is highly recommended that the users review Appendix A of the APSLD Handbook before using the APSLD calculator. A quick comparison of the two primary traffic data sources is noted in the Table below.
• Statewide Planning Map – Presents traffic data in a linear format. Appropriate for use where directionality on the main lanes is not a consideration. Examples: A segment of a highway where the work zone involves traffic in both directions, or a work zone that only involves a frontage roadbed.
• STARS II – Presents traffic data in a point format. Appropriate for use where directionality is needed on the main lanes or where data is needed for specific traffic stations. Examples: A segment of a highway where the work zone only involves the southbound roadbed, or a work zone at an intersection where individual traffic stations need to be identified.
• Traffic Modeling from district staff or a consultant – Appropriate when the Statewide Planning Map or STARS II are not sufficient to determine the traffic data within the work zone limits. Example: A complex interchange of two highways in a metro area. Numerous connectors and ramps make a simple analysis impossible.
Statewide Planning Map Overview
Available at the following URL:
https://www.txdot.gov/apps/statewide_mapping/StatewidePlanningMap.html
The "AADT" overlay on the Statewide Planning Map is not recommended for the purpose of RUC calculation because it combines mainlanes and frontage AADT into a single value. Furthermore, data are presented in point format (based on traffic stations), and additional analysis is required to determine the correct AADT value between any two given points. The "Roadway Inventory – On-System Roadbeds" overlay is recommended for the purpose of RUC calculation instead of the "AADT" overlay. The certified annual Roadway Inventory file is the source of data for this overlay.
Using the “Roadway Inventory – On-System Roadbeds” overlay to obtain traffic data from the Statewide Planning Map
Traffic data are presented in a linear format (coded to TxDOT linework). With the "Roadway Inventory - On-System Roadbeds" overlay selected, any On-System roadbed can be selected in the map. The resulting pop-up displays multiple Roadway Inventory data items for the extent of the highlighted linework segment. These include the necessary "AADT" figure (the most current year available) and "Truck Percent." AADT is combined across mainlanes (bi-directional). Selecting the right or left roadbed of a divided highway will display the total AADT for both directions on the mainlanes. If AADT is needed for a single direction only, an analysis of traffic data in the STARS II system will be necessary. Please see the next section, "STARS II Overview and Traffic Data Support." Right and left frontage roads have unique AADT values in the "Roadway Inventory - On-System Roadbeds" overlay and can be evaluated separately from the mainlanes, if relevant to a construction project. To calculate the AADT of trucks only, multiply AADT by the Truck Percent for a given segment. The resulting "Truck AADT" can be subtracted from the total AADT to derive the "Car AADT" as required for the RUC calculation. NOTE: A construction project may include multiple Roadway Inventory segments within its limits. If there are multiple AADT values to consider within the project limits, professional judgement will be necessary to determine the most appropriate value. One option is to use the predominant AADT value, based on length, within the project limits. If there is no clear predominant value, a simple approach is to use the highest AADT value within the project limits. There may also be instances in which an average, weighted by segment length, could be considered. However, due to the complexities associated with the overlap of Roadway Inventory traffic segments, multiple AADT assignments, and project specific limits, a weighted average method might be more challenging to use.
STARS II Overview and Traffic Data Support
The STARS II system is necessary for obtaining directional traffic data. This is because the Statewide Planning Map only represents bi-directional (two way) traffic data on the mainlanes. STARS II is available at the following URL:
txdot.ms2soft.com
Traffic data are presented in a point format (based upon traffic stations). Using the STARS II system and correctly interpreting traffic data requires training beyond the scope of this overview. STARS II training and support are available—Please contact the TPP Traffic Analysis Section System Support Data Liaison at:
TPP_RUCLD.AADT@txdot.gov
Please note that RUC calculations rely on certified AADT values. Other volume data available within STARS II are not recommended, as these data are not reflective of the certified and published AADT figures. Seasonal factors in STARS II are specifically applied to annualize short-term counts, and time factors do not exist in STARS II. Therefore, neither would be recommended for the purpose of RUC calculations.

## Reduced_Speed
Work Zone Road Users Costs
Reduced Speed Scenario
Project Information
CSJ:
Highway / Roadway:
County:
District:
| Project Letting Year: | 2024
Inputs
|  | Car | Truck
AADT of Section:
Length of the Work Zone (Miles):
Original Posted Speed (MPH):
Work Zone Speed (MPH):
Duration of Work Zone (Days):
Calculations
| Hourly Value of Time: | 37.2 | 52.75
| Travel Time Posted Speed (Secs): | #DIV/0! | #DIV/0!
| Travel Time Work Zone Speed (Secs): | #DIV/0! | #DIV/0!
| Additional Travel Time (Secs): | #DIV/0! | #DIV/0! | #DIV/0!
| Additional Travel Time (Hours): | #DIV/0! | #DIV/0!
| Delay Cost per Vehicle: | #DIV/0! | #DIV/0!
| Delay Cost per Day: | #DIV/0! | #DIV/0!
| Delay Cost for Work Zone Duration: | #DIV/0! | #DIV/0!
| Total Delay Cost for Work Zone Duration: | #DIV/0!
Results
| Average Delay Cost per Day: | #DIV/0!
1 | Fill in all the Highlighted Cells
2 | The Average Delay Cost / Day is the Road Users Cost for this scenario.
3 | Instructions for obtaining traffic data (ADT) can be found on the Traffic_Data tab.

## Increased Travel_Time
Work Zone Road Users Costs
Detour resulting in Additional Travel Time using Increased Travel Time
Project Information
CSJ:
Highway / Roadway:
County:
District:
| Project Letting Year: | 2024
Inputs
|  | Car | Truck
AADT of Detoured Section:
Time to Drive the Roadway Section (Mins):
Time to drive the detour or work zone (Mins):
Duration of Work Zone (Days):
Calculations
| Hourly Value of Time: | 37.2 | 52.75
| Delay (Mins): | 0 | 0
| Delay (Hours): | 0 | 0
| Delay Cost per Vehicle ($): | 0 | 0
| Delay Cost per Day ($): | 0 | 0
| Delay Cost for Work Zone Duration: | 0 | 0
| Total Delay Cost for Work Zone Duration: | 0
Results
| Average Delay Cost per Day: | #DIV/0!
1 | Fill in all the Highlighted Cells
2 | The Average Delay Cost / Day is the Road Users Cost for this scenario.
3 | Instructions for obtaining traffic data (ADT) can be found on the Traffic_Data tab.

## Detour_Distance
Work Zone Road Users Costs
Detour resulting in Additional Distance and Different Speed
Project Information
CSJ:
Highway / Roadway:
County:
District:
| Project Letting Year: | 2024
Inputs
|  | Car | Truck
AADT of Detoured Section:
Length of the normal route (Miles):
Length of the detour route (Miles):
Posted speed on normal route (MPH):
Posted speed on detour route (MPH):
Duration of Work Zone (Days):
Calculations
| Hourly Value of Time: | 37.2 | 52.75
| Travel time along normal route (Secs): | #DIV/0! | #DIV/0!
| Travel time along detour route (Secs): | #DIV/0! | #DIV/0!
| Delay (Secs): | #DIV/0! | #DIV/0!
| Delay (Hours): | #DIV/0! | #DIV/0!
| Delay Cost per vehicle ($): | #DIV/0! | #DIV/0!
| Delay Cost per Day ($): | #DIV/0! | #DIV/0!
| Delay Cost for Work Zone Duration: | #DIV/0! | #DIV/0!
| Total Delay Cost for Work Zone Duration: | #DIV/0!
| Vehicle Operating Costs ($/miles): | 0.56 | 0.67
| Additional Miles from detour (Veh-Miles): | 0 | 0
| Additional Vehicle Operating Costs ($): | 0 | 0
| Additional Vehicle Operating Costs ($): | 0
Results
| Average Road Users Cost per Day ($): | #DIV/0!
1 | Fill in all the Highlighted Cells
2 | The Average Delay Cost / Day is the Road Users Cost for this scenario.
3 | Instructions for obtaining traffic data (ADT) can be found on the Traffic_Data tab.

## VOT
2024-03-19
CPI Year | Semiannual Average | Annual Avg | % change from 2013 | Letting Year | User Cost / Hour |  |  | VOC (per mile) |  | Actual Growth in VOT
[5 empty] | Car | Truck |  | Car | Truck | Car | Truck
2013 |  |  |  | 2014 | 21.42 | 31.28 | Actual
2014 |  |  |  | 2015 | 21.73 | 31.71 |  |  |  | 1.447% | 1.375%
2015 |  |  |  | 2016 | 22.09 | 32.26 |  |  |  | 1.657% | 1.734%
2016 |  |  |  | 2017 | 22.12 | 32.3 |  |  |  | 0.1358% | 0.124%
2017 |  |  |  | 2018 | 28.69 | 36.28 |  | 0.582 | 1.035 | 29.7% | 12.32%
2018 |  |  |  | 2019 | 29.35 | 39.47 |  | 0.582 | 1.035 | 2.3% | 8.793%
2019 |  |  |  | 2020 | 30.12 | 41.33 |  | 0.582 | 1.035 | 2.624% | 4.712%
2020 |  |  |  | 2021 | 30.54 | 41.91 |  | 0.582 | 1.035 | 1.394% | 1.403%
2021 |  |  |  | 2022 | 32.83 | 45.05 |  | 0.585 | 1.035 | 7.498% | 7.492%
2022 |  |  |  | 2023 | 34.9344 | 47.9377 |  | 0.7 | 1.025 | 6.41% | 6.41%
2023 |  |  |  | 2024 | 37.2 | 52.75 |  | 0.56 | 0.67 | 6.485% | 10.04%
2024 |  |  |  | 2025 | 37.944 | 53.805 | Estimated at 2% | 0.56 | 0.67 | 2% | 2%
2025 |  |  |  | 2026 | 38.7029 | 54.8811 |  | 0.56 | 0.67 | 2% | 2%
2026 |  |  |  | 2027 | 39.4769 | 55.9787 |  | 0.56 | 0.67 | 2% | 2%
2027 |  |  |  | 2028 | 40.2665 | 57.0983 |  | 0.56 | 0.67 | 2% | 2%
2028 |  |  |  | 2029 | 41.0718 | 58.2403 |  | 0.56 | 0.67 | 2% | 2%
2029 |  |  |  | 2030 | 41.8932 | 59.4051 |  | 0.56 | 0.67 | 2% | 2%
2030 |  |  |  | 2031 | 42.7311 | 60.5932 |  | 0.56 | 0.67 | 2% | 2%
2031 |  |  |  | 2032 | 43.5857 | 61.805 |  | 0.56 | 0.67 | 2% | 2%
2032 |  |  |  | 2033 | 44.4574 | 63.0411 |  | 0.56 | 0.67 | 2% | 2%
2033 |  |  |  | 2034 | 45.3466 | 64.302 |  | 0.56 | 0.67 | 2% | 2%
2034 |  |  |  | 2035 | 46.2535 | 65.588 |  | 0.56 | 0.67 | 2% | 2%
2035 |  |  |  | 2036 | 47.1786 | 66.8998 |  | 0.56 | 0.67 | 2% | 2%

## CodeChart 03
Last Update: 08/30/17
Code Chart 03
D/D/O Computer Codes / Acronyms and Descriptions
D/D/O
Computer Code | Acronym | Description
8 | ABL | Abilene District
4 | AMA | Amarillo District
19 | ATL | Atlanta District
14 | AUS | Austin District
20 | BMT | Beaumont District
17 | BRY | Bryan District
23 | BWD | Brownwood District
25 | CHS | Childress District
16 | CRP | Corpus Christi District
18 | DAL | Dallas District
24 | ELP | El Paso District
2 | FTW | Fort Worth District
12 | HOU | Houston District
5 | LBB | Lubbock District
11 | LFK | Lufkin District
22 | LRD | Laredo District
6 | ODA | Odessa District
1 | PAR | Paris District
21 | PHR | Pharr District
15 | SAT | San Antonio District
7 | SJT | San Angelo District
10 | TYL | Tyler District
9 | WAC | Waco District
3 | WFS | Wichita Falls District
13 | YKM | Yoakum District

## Table 1
Last Updated:04/01/1999
Code Chart 04-xref
County Number/Name With Corresponding District Number
County Number | County Name | District Number | District
1 | Anderson | 10 | TYL
2 | Andrews | 6 | ODA
3 | Angelina | 11 | LFK
4 | Aransas | 16 | CRP
5 | Archer | 3 | WFS
6 | Armstrong | 4 | AMA
7 | Atascosa | 15 | SAT
8 | Austin | 13 | YKM
9 | Bailey | 5 | LBB
10 | Bandera | 15 | SAT
11 | Bastrop | 14 | AUS
12 | Baylor | 3 | WFS
13 | Bee | 16 | CRP
14 | Bell | 9 | WAC
15 | Bexar | 15 | SAT
16 | Blanco | 14 | AUS
17 | Borden | 8 | ABL
18 | Bosque | 9 | WAC
19 | Bowie | 19 | ATL
20 | Brazoria | 12 | HOU
21 | Brazos | 17 | BRY
22 | Brewster | 24 | ELP
23 | Briscoe | 25 | CHS
24 | Brooks | 21 | PHR
25 | Brown | 23 | BWD
26 | Burleson | 17 | BRY
27 | Burnet | 14 | AUS
28 | Caldwell | 14 | AUS
29 | Calhoun | 13 | YKM
30 | Callahan | 8 | ABL
31 | Cameron | 21 | PHR
32 | Camp | 19 | ATL
33 | Carson | 4 | AMA
34 | Cass | 19 | ATL
35 | Castro | 5 | LBB
36 | Chambers | 20 | BMT
37 | Cherokee | 10 | TYL
38 | Childress | 25 | CHS
39 | Clay | 3 | WFS
40 | Cochran | 5 | LBB
41 | Coke | 7 | SJT
42 | Coleman | 23 | BWD
43 | Collin | 18 | DAL
44 | Collingsworth | 25 | CHS
45 | Colorado | 13 | YKM
46 | Comal | 15 | SAT
47 | Comanche | 23 | BWD
48 | Concho | 7 | SJT
49 | Cooke | 3 | WFS
50 | Coryell | 9 | WAC
51 | Cottle | 25 | CHS
52 | Crane | 6 | ODA
53 | Crockett | 7 | SJT
54 | Crosby | 5 | LBB
55 | Culberson | 24 | ELP
56 | Dallam | 4 | AMA
57 | Dallas | 18 | DAL
58 | Dawson | 5 | LBB
59 | Deaf Smith | 4 | AMA
60 | Delta | 1 | PAR
61 | Denton | 18 | DAL
62 | DeWitt | 13 | YKM
63 | Dickens | 25 | CHS
64 | Dimmitt | 22 | LRD
65 | Donley | 25 | CHS
66 | Kenedy | 21 | PHR
67 | Duval | 22 | LRD
68 | Eastland | 23 | BWD
69 | Ector | 6 | ODA
70 | Edwards | 7 | SJT
71 | Ellis | 18 | DAL
72 | El Paso | 24 | ELP
73 | Erath | 2 | FTW
74 | Falls | 9 | WAC
75 | Fannin | 1 | PAR
76 | Fayette | 13 | YKM
77 | Fisher | 8 | ABL
78 | Floyd | 5 | LBB
79 | Foard | 25 | CHS
80 | Fort Bend | 12 | HOU
81 | Franklin | 1 | PAR
82 | Freestone | 17 | BRY
83 | Frio | 15 | SAT
84 | Gaines | 5 | LBB
85 | Galveston | 12 | HOU
86 | Garza | 5 | LBB
87 | Gillespie | 14 | AUS
88 | Glasscock | 7 | SJT
89 | Goliad | 16 | CRP
90 | Gonzales | 13 | YKM
91 | Gray | 4 | AMA
92 | Grayson | 1 | PAR
93 | Gregg | 10 | TYL
94 | Grimes | 17 | BRY
95 | Guadalupe | 15 | SAT
96 | Hale | 5 | LBB
97 | Hall | 25 | CHS
98 | Hamilton | 9 | WAC
99 | Hansford | 4 | AMA
100 | Hardeman | 25 | CHS
101 | Hardin | 20 | BMT
102 | Harris | 12 | HOU
103 | Harrison | 19 | ATL
104 | Hartley | 4 | AMA
105 | Haskell | 8 | ABL
106 | Hays | 14 | AUS
107 | Hemphill | 4 | AMA
108 | Henderson | 10 | TYL
109 | Hidalgo | 21 | PHR
110 | Hill | 9 | WAC
111 | Hockley | 5 | LBB
112 | Hood | 2 | FTW
113 | Hopkins | 1 | PAR
114 | Houston | 11 | LFK
115 | Howard | 8 | ABL
116 | Hudspeth | 24 | ELP
117 | Hunt | 1 | PAR
118 | Hutchinson | 4 | AMA
119 | Irion | 7 | SJT
120 | Jack | 2 | FTW
121 | Jackson | 13 | YKM
122 | Jasper | 20 | BMT
123 | Jeff Davis | 24 | ELP
124 | Jefferson | 20 | BMT
125 | Jim Hogg | 21 | PHR
126 | Jim Wells | 16 | CRP
127 | Johnson | 2 | FTW
128 | Jones | 8 | ABL
129 | Karnes | 16 | CRP
130 | Kaufman | 18 | DAL
131 | Kendall | 15 | SAT
132 | Kent | 8 | ABL
133 | Kerr | 15 | SAT
134 | Kimble | 7 | SJT
135 | King | 25 | CHS
136 | Kinney | 22 | LRD
137 | Kleberg | 16 | CRP
138 | Knox | 25 | CHS
139 | Lamar | 1 | PAR
140 | Lamb | 5 | LBB
141 | Lampasas | 23 | BWD
142 | La Salle | 22 | LRD
143 | Lavaca | 13 | YKM
144 | Lee | 14 | AUS
145 | Leon | 17 | BRY
146 | Liberty | 20 | BMT
147 | Limestone | 9 | WAC
148 | Lipscomb | 4 | AMA
149 | Live Oak | 16 | CRP
150 | Llano | 14 | AUS
151 | Loving | 6 | ODA
152 | Lubbock | 5 | LBB
153 | Lynn | 5 | LBB
154 | Madison | 17 | BRY
155 | Marion | 19 | ATL
156 | Martin | 6 | ODA
157 | Mason | 14 | AUS
158 | Matagorda | 13 | YKM
159 | Maverick | 22 | LRD
160 | McCulloch | 23 | BWD
161 | McLennan | 9 | WAC
162 | McMullen | 15 | SAT
163 | Medina | 15 | SAT
164 | Menard | 7 | SJT
165 | Midland | 6 | ODA
166 | Milam | 17 | BRY
167 | Mills | 23 | BWD
168 | Mitchell | 8 | ABL
169 | Montague | 3 | WFS
170 | Montgomery | 12 | HOU
171 | Moore | 4 | AMA
172 | Morris | 19 | ATL
173 | Motley | 25 | CHS
174 | Nacogdoches | 11 | LFK
175 | Navarro | 18 | DAL
176 | Newton | 20 | BMT
177 | Nolan | 8 | ABL
178 | Nueces | 16 | CRP
179 | Ochiltree | 4 | AMA
180 | Oldham | 4 | AMA
181 | Orange | 20 | BMT
182 | Palo Pinto | 2 | FTW
183 | Panola | 19 | ATL
184 | Parker | 2 | FTW
185 | Parmer | 5 | LBB
186 | Pecos | 6 | ODA
187 | Polk | 11 | LFK
188 | Potter | 4 | AMA
189 | Presidio | 24 | ELP
190 | Rains | 1 | PAR
191 | Randall | 4 | AMA
192 | Reagan | 7 | SJT
193 | Real | 7 | SJT
194 | Red River | 1 | PAR
195 | Reeves | 6 | ODA
196 | Refugio | 16 | CRP
197 | Roberts | 4 | AMA
198 | Robertson | 17 | BRY
199 | Rockwall | 18 | DAL
200 | Runnels | 7 | SJT
201 | Rusk | 10 | TYL
202 | Sabine | 11 | LFK
203 | San Augustine | 11 | LFK
204 | San Jacinto | 11 | LFK
205 | San Patricio | 16 | CRP
206 | San Saba | 23 | BWD
207 | Schleicher | 7 | SJT
208 | Scurry | 8 | ABL
209 | Shackelford | 8 | ABL
210 | Shelby | 11 | LFK
211 | Sherman | 4 | AMA
212 | Smith | 10 | TYL
213 | Somervell | 2 | FTW
214 | Starr | 21 | PHR
215 | Stephens | 23 | BWD
216 | Sterling | 7 | SJT
217 | Stonewall | 8 | ABL
218 | Sutton | 7 | SJT
219 | Swisher | 5 | LBB
220 | Tarrant | 2 | FTW
221 | Taylor | 8 | ABL
222 | Terrell | 6 | ODA
223 | Terry | 5 | LBB
224 | Throckmorton | 3 | WFS
225 | Titus | 19 | ATL
226 | Tom Green | 7 | SJT
227 | Travis | 14 | AUS
228 | Trinity | 11 | LFK
229 | Tyler | 20 | BMT
230 | Upshur | 19 | ATL
231 | Upton | 6 | ODA
232 | Uvalde | 15 | SAT
233 | Val Verde | 22 | LRD
234 | Van Zandt | 10 | TYL
235 | Victoria | 13 | YKM
236 | Walker | 17 | BRY
237 | Waller | 12 | HOU
238 | Ward | 6 | ODA
239 | Washington | 17 | BRY
240 | Webb | 22 | LRD
241 | Wharton | 13 | YKM
242 | Wheeler | 25 | CHS
243 | Wichita | 3 | WFS
244 | Wilbarger | 3 | WFS
245 | Willacy | 21 | PHR
246 | Williamson | 14 | AUS
247 | Wilson | 15 | SAT
248 | Winkler | 6 | ODA
249 | Wise | 2 | FTW
250 | Wood | 10 | TYL
251 | Yoakum | 5 | LBB
252 | Young | 3 | WFS
253 | Zapata | 21 | PHR
254 | Zavala | 22 | LRD